## HMI FROP HMI Releases Updated
| Software Freeze |  |  |  | 2019-01-18 | 2019-03-08 | 2019-04-26 | 2019-06-14 | 2019-08-09 | 2019-09-27 | 2019-11-15 | 2020-01-17 | 2020-03-06 | 2020-04-24 | 2020-06-12 | 2020-08-07 | 2020-09-25
| Software Release |  |  |  | 2019-02-01 | 2019-03-22 | 2019-05-10 | 2019-06-28 | 2019-08-23 | 2019-10-11 | 2019-11-29 | 2020-01-31 | 2020-03-20 | 2020-05-08 | 2020-06-26 | 2020-08-21 | 2020-10-09
| HMI Release to Platform team |  |  |  | 2019-01-30 | 2019-03-08 | 2019-04-26 | 2019-06-14 | 2019-08-09 | 2019-09-27 | 2019-11-15 | 2020-01-17 | 2020-03-06 | 2020-04-24 | 2020-06-12 | 2020-08-07 | 2020-09-25
| Release Cadence |  |  |  | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155
Domain | Sub-Domain | HMI Rel | HMI Rel Date | Platform Del | 2019-03-08: IV-B; 2019-06-14: IV-V; 2019-11-15: 65% BOR; 2020-04-24: 80% BOR; 2020-09-25: VTC
APA | Automated Parking Assist | 146 | 2019-06-14 | 146 | 2019-06-14: R; 2019-08-09: D; 2019-09-27: C
Camera | Camera | 146 | 2019-06-14 | 145 | 2019-06-14: R; 2019-08-09: D; 2019-09-27: C
Cluster | Navigation in cluster - Google Maps | TBD | TBD
Favorites | Audio Favorites | 144 | 2019-03-08 |  | 2019-03-08: R; 2019-06-14: D; 2019-09-27: C
Favorites | Phone Favorites | 144 | 2019-03-08 |  | 2019-03-08: R; 2019-06-14: D; 2019-09-27: C
GM Air Quality |  | N/A | N/A | 143
GM Audio | Now Playing (Radio - AM, FM) | 144 | 2019-03-08 | 143 | 2019-03-08: R; 2019-06-14: D; 2019-09-27: C
GM Audio | Now Playing (Media - USB, SD, BT, MYMedia, iPod, Aux) | 144 | 2019-03-08 | 143 | 2019-03-08: R; 2019-06-14: D; 2019-09-27: C
GM Audio | Now Playing (SXM, DAB) | 145 | 2019-04-26 | 143 | 2019-04-26: R; 2019-08-09: D; 2019-09-27: C
GM Audio | Now Playing (Projection - Carplay, Android Auto, Mirror Link) | 145 | 2019-04-26 | 143 | 2019-04-26: R; 2019-08-09: D; 2019-09-27: C
GM Audio | Now Playing (Apps - Spotify) | 145 | 2019-04-26 | 143 | 2019-04-26: R; 2019-08-09: D; 2019-09-27: C
GM Audio | Sources - Favorite | 144 | 2019-03-08 | 143 | 2019-03-08: R; 2019-06-14: D; 2019-09-27: C
GM Audio | Sources - Settings | 144 | 2019-03-08 | 145 | 2019-03-08: R; 2019-06-14: D; 2019-09-27: C
GM Audio | Sources - Browse (Radio, Media, Apps, Projection) | 145 | 2019-04-26 | 147 | 2019-04-26: R; 2019-08-09: D; 2019-09-27: C
GM CarPlay | Connect to Apple CarPlay device | 145 | 2019-04-26 | 144 | 2019-04-26: R; 2019-06-14: D; 2019-09-27: C
GM GAL | Connect to a Android Device | 145 | 2019-04-26 | 144 | 2019-04-26: R; 2019-06-14: D; 2019-09-27: C
System UI | Widget Library | 143 | 2019-01-30 | 144 | 2019-01-30: R ü
GM Phone | Active Call | 143 | 2019-01-30 | 144 | 2019-01-30: R ü; 2019-04-26: D; 2019-09-27: C
GM Phone | Favorites | 143 | 2019-01-30 | 144 | 2019-01-30: R ü; 2019-04-26: D; 2019-09-27: C
GM Phone | Recents | 143 | 2019-01-30 | 144 | 2019-01-30: R ü; 2019-04-26: D; 2019-09-27: C
GM Phone | Contacts | 143 | 2019-01-30 | 144 | 2019-01-30: R ü; 2019-04-26: D; 2019-09-27: C
GM Phone | Settings | 144 | 2019-03-08 | 144 | 2019-03-08: R; 2019-06-14: D; 2019-09-27: C
GM Phone | Keypad - Incoming Call | 144 | 2019-03-08 | 145 | 2019-03-08: R; 2019-06-14: D; 2019-09-27: C
GM Phone | Keypad - No Phone Screen | 144 | 2019-03-08 | 145 | 2019-03-08: R; 2019-06-14: D; 2019-09-27: C
GM Phone | Keypad - Multi-phone
GM Phone | Keypad - MFC | N/A | N/A | N/A
GM Phone | Keypad - Projection | N/A | N/A | 145
GM Phone | Keypad - Download Restrictions | N/A | N/A | 145
GM Phone | Keypad - OnStar TTY | 145 | 2019-04-26 | 145 | 2019-04-26: R; 2019-08-09: D; 2019-09-27: C
GM Phone | Active Call Cluster/HUD |  |  | 146
GM Phone | Cluster/HUD |  |  | 146
GM Seat Status Pane | Driver Seat controls list |  |  | 144
GM Seat Status Pane | Passenger Seat Controls List |  |  | 144
GM Seat Status Pane | Notifications |  |  | 144
GM Settings | Vehicle Tab | 144 | 2019-03-08 | 143 | 2019-03-08: R; 2019-06-14: D; 2019-09-27: C
GM Settings | Apps Tab | 145 | 2019-04-26 | 143 | 2019-04-26: R; 2019-08-09: D; 2019-09-27: C
GM Settings | Personal | 146 | 2019-06-14 | 146 | 2019-06-14: R; 2019-08-09: D; 2019-09-27: C
GM Settings | System Tab - Display/Sounds | 146 | 2019-06-14 | 146 | 2019-06-14: R; 2019-08-09: D; 2019-09-27: C
GM Settings | System Tab - Wifi | 145 | 2019-04-26 | 145 | 2019-04-26: R; 2019-08-09: D; 2019-09-27: C
GM Settings | System Tab - BT | 145 | 2019-04-26 | 145 | 2019-04-26: R; 2019-08-09: D; 2019-09-27: C
GM Settings | System Tab - Phone | 145 | 2019-04-26 | 145 | 2019-04-26: R; 2019-08-09: D; 2019-09-27: C
GM Settings | System Tab - Others | 145 | 2019-04-26 | 145 | 2019-04-26: R; 2019-08-09: D; 2019-09-27: C
GM Settings | Lic Content Mgr (LCM) |  |  | 144
GM VR | Voice commands implementation | N/A | N/A | TBD
Home Screen | Porch View |  |  | 144
Home Screen | Installed Apps |  |  | 145
Home Screen | Dynamic Data |  |  | 146
Home Screen | Data Persistance |  |  | 147
HTML Viewer | HTML Viewer |  |  | 143 | bar: 2020-01-17 to 2020-09-25
HVAC | Front Climate | 144 | 2019-01-30 | 143 | 2019-03-08: R; 2019-06-14: D; 2019-09-27: C
HVAC | Rear Climate | 144 | 2019-03-08 | 143 | 2019-03-08: R; 2019-06-14: D; 2019-09-27: C
HVAC | Climate Settings | 145 | 2019-04-26 | 143 | 2019-04-26: R; 2019-08-09: D; 2019-09-27: C
OnStar TbT | OnStar TbT | 146 | 2019-06-14 | N/A | 2019-06-14: R; 2019-08-09: D; 2019-09-27: C
OnStar UI | OnStar UI | 146 | 2019-06-14 | N/A | 2019-06-14: R; 2019-08-09: D; 2019-09-27: C
Personalization | UI/UX plans on providing designs
Teen Mode | Teen Driver Volume Status Pane | 146 | 2019-06-14 | 145 | 2019-06-14: R; 2019-08-09: D; 2019-09-27: C
Teen Mode | Teen Driver Register Key | 146 | 2019-06-14 | 145 | 2019-06-14: R; 2019-08-09: D; 2019-09-27: C
Trailering | Basic Setup | 144 | 2019-03-08 | 143 | 2019-03-08: R; 2019-06-14: D; 2019-09-27: C
Trailering | Edit Trailer Profile | 146 | 2019-06-14 | 144 | 2019-06-14: R; 2019-08-09: D; 2019-09-27: C
Trailering | Settings | 144 | 2019-03-08 | 143 | 2019-03-08: R; 2019-06-14: D; 2019-09-27: C
Trailering | Trailer Profile(Add) | 144 | 2019-03-08 | 143 | 2019-03-08: R; 2019-06-14: D; 2019-09-27: C
Trailering | Advanced Setup+ (Tow/Haul Mode, Maintenance Reminders, TTPS, ) | 145 | 2019-04-26 | 144 | 2019-04-26: R; 2019-08-09: D; 2019-09-27: C
Trailering | Status View (Trailer, Vehicle, Connections, Maintenance, Guest, More ) | 146 | 2019-06-14 | 144 | 2019-06-14: R; 2019-08-09: D; 2019-09-27: C
Trailering | Reminders | 145 | 2019-01-30 | 144 | 2019-04-26: R; 2019-08-09: D; 2019-09-27: C
Trailering | Camera/Towing Assistance | 146 | 2019-06-14 | 143 | 2019-06-14: R; 2019-08-09: D; 2019-09-27: C
Trailering | Check List (Conventional, GooseNeck, FifthWheel) | 145 | 2019-04-26 | 143 | 2019-04-26: R; 2019-08-09: D; 2019-09-27: C
Trailering | Vehicle Data | 145 | 2019-04-26 | 144 | 2019-04-26: R; 2019-08-09: D; 2019-09-27: C
Trailering | Lights & Electric Brakes | 145 | 2019-04-26 | 144 | 2019-04-26: R; 2019-08-09: D; 2019-09-27: C
Trailering | Diagnostics | 145 | 2019-04-26 | 144 | 2019-04-26: R; 2019-08-09: D; 2019-09-27: C
Trailering | Trailer Profile (import/export) | 146 | 2019-06-14 |  | 2019-06-14: R; 2019-08-09: D; 2019-09-27: C
Trailering | User Switch (trailer profile switch) | 146 | 2019-06-14 | 145 | 2019-06-14: R; 2019-08-09: D; 2019-09-27: C
Trailering | Back Office | N/A | N/A | 145
Updater | UI/UX plans on providing designs
Valet Mode | Valet Mode | 146 | 2019-06-14 | 145 | 2019-06-14: R; 2019-08-09: D; 2019-09-27: C
[5 empty] | R | Ready - HMI development is complete - MY22 API (Features commented out to be non-functional until integration with the main line is coordinated)
[5 empty] | D | Done - HMI tested with MY22 platform API (grahics not final)
[5 empty] | C | Complete - HMI with final graphics (minor graphics refinement will continue until VTC)
Note on B11: Carr, Daryl: OOO for MY22
Note on B30: Carr, Daryl: Pending CR
Note on B31: Carr, Daryl: OOO for MY22
Note on B48: Carr, Daryl: HMI aligned with GIS-509
Note on B58: Carr, Daryl: Is this HMI only?
Note on B59: Carr, Daryl: Is this HMI only?